## Product Backlog
PRODUCT BACKLOG ID | PRIORITY | USER STORY ID | USER STORIES | SCURM TEAM ASSIGNED | ASSIGNED TO | STATUS | REMARKS
SPRINT-1 USER AUTHENTICATION
P001 | high | ID-001 | login | Admin team | yashasree | completed | NO
P002 | medium | ID-002 | username | Admin team
P003 | high | ID-003 | password | Admin team
SPRINT-2 Movie Search and Selection
P004 | high | ID-004 | movie search | Developer team | Sai charan | completed
P005 | high | ID-005 | movie selection | Developer team |  |  | NO
SPRINT-3 Showtime and Seat Selection
P006 | high | ID-006 | showtime selection | Developer team | likitha | completed | NO
P007 | high | ID-007 | seat selection | Developer team
SPRINT-4 Booking and Payment
P008 | medium | ID-008 | booking ticket | Developer team | lahari | completed | NO
P009 | high | ID-009 | manage booking | Developer team
P010 | high | ID-010 | payment | Developer team
SPRINT-5 Cancellation and refund
P011 | high | ID-11 | cancel booking | cancellation team | sravya | Inprogress | NO
P012 | high | ID-12 | process refund | cancellation team |  | completed | NO
SPRINT-6 Notifications
P013 | medium | ID-14 | notifications | notification team | divya | completed | NO

## Sprint backlog
USER STORY ID | USER STORY NAME | USER STORY STEP DEFINITION |  |  | ASSIGNED TO | ESTIMATED TIME | ACTUAL TIME | STATUS | REMARKS
|  | AS A<type of user> | I WANT TO <perform some task> | SO THAT I CAN <achieve some goal>
P001 | login | user-001 | Navigate to Login Page | The user accesses the login page of the online movie ticket booking platform. | Yashasree | 10hours | 8hours | completed | NO
It access my account and manage my bookings
P002 | username | user-002 | Enter username | The user enters their registered username into the respective fields. | Yashasree |  |  | completed
Authenticate credentials securely.
the user gains access to their personalized account dashboard.
P003 | password | user-003 | Enter password | The user enters their registered password into the respective fields. | Yashasree |  |  | completed
The system verifies the entered credentials against the stored user data.
P004 | Movie search | user-004 | I want to search for movies | The user navigates to the search feature provided on the platform, typically located on the homepage or in the movie section. | Sai charan | 6 hours | 4 hours | completed | Provide search filters for genres, ratings, and showtimes
The user enters keywords, such as movie title, genre, actor, or director, into the search bar.
The user can click on individual movie titles from the search results to view detailed information
P005 | movie selection | user-005 | I want to select a movie | Choose Movie: From the list of available movies, the user clicks on the desired movie they want to watch. | Sai charan | 5 hours | 3 hours | completed | Display detailed movie information such as synopsis, cast, and ratings.
View Movie Details: The user is directed to the movie details page, where they can explore additional information about the selected movie.
P006 | Show time selection | user-006 | I want to select a showtime | Browse Showtimes: The user is presented with a list of available showtimes for the selected movie. | likitha | 5 hours | 4 hours | completed | Show available showtimes for each day.
Choose Showtime: The user selects a preferred showtime from the available options, considering factors such as date, time, and theater location.
Confirm Selection: After choosing the desired showtime, the user confirms their selection to proceed with the booking process.
P006 | screen selection | user-007 | I want to select seats | View Seat Availability: The user can see which seats are available and which are already booked by other users. | likitha | 10 hours | 9 hours | completed | Provide real-time seat availability.
Select Seats: The user clicks on the available seats to choose their preferred seating arrangement, considering factors like proximity to the screen, aisle seats, or specific rows.
P008 | booking ticket | user-008 | I want to book a ticket | Confirm Booking Details: The user reviews the selected movie, showtime, and seat choices to ensure they are accurate. | lahari | 15 hours | 10 hours | completed | Ensure booking confirmation and receipt generation.
Provide Personal Information: The user enters their personal details, such as name, contact information, and any special requests.
P009 | manage booking | user-009 |  | The user navigates to the "My Bookings" section of their account dashboard. | lahari | 10 hours | 8 hours | completed | Provide options for modifying or canceling bookings.
The user selects the booking they want to modify and chooses the appropriate action, such as changing the showtime or seats
P010 | payment | user-010 |  | Select Payment Method: The user chooses a preferred payment method from the available options, such as credit card, debit card, or digital wallet. | Lahari | 24 hours | 22 hours | completed | NO
The user enters payment details and confirms the transaction to finalize the booking.
P011 | Cancel Booking | user-011 | I want to cancel booking tickets | the user can opt to cancel the booking, following the cancellation process provided by the platform. | Sravya | 20 hours | 18 hours | Inprogress | Ensure the refund process is clear and efficient.
Receive Confirmation: After making any changes or cancellations, the user receives a confirmation message regarding the updated status of their booking.
The user may be prompted to select a reason for the cancellation from a dropdown menu or provide additional comments.
P012 | Process refund | user-012 | I want to process a refund | The user submits the cancellation request, which is then processed by the system. | Sravya | 15 hours | 14 hours | completed | NO
The refund amount is reversed to the original payment method used during the booking (e.g., credit card, debit card, digital wallet).
ID-13 | Notification Team | user-013 | I want to send timely notifications | the notification dashboard where all user interactions and upcoming schedules are managed. | Divya | 10 hours | 8 hours | completed | Implement email and SMS notifications.
Identify events that require notifications, such as booking confirmations, reminders, cancellations, and special promotions.
Use the system to send out notifications automatically based on the schedule and user actions.